## Basic Template
|  |  |  | Project Leader: |  | Homer Simpson |  | Project: |  | That Tank Game in 3D | [12 empty] | Date: 01/01/2010
Project Objective: To develop two demo levels of the Tank Game
Objectives |  |  |  |  | Major Tasks |  |  | Project Completed By: 04/3/2010 | [11 empty] | Owner
O |  |  |  | 1 | Storyboards completed |  |  | O | [11 empty] | A | B | B | B
O |  |  |  | 2 | Gameplay, UI, powerups, feature set defined |  |  |  | O | [10 empty] | A | B | B | B
| O |  |  | 3 | Initial placeholder graphical asset created |  |  |  |  | O | [9 empty] | A
| O |  |  | 4 | Mid semester graphical asset created | [6 empty] | O | [7 empty] | A
|  | O |  | 5 | Final graphical asset created | [9 empty] | O |  |  |  |  | A
| O |  |  | 6 | Initial placeholder audio asset created |  |  |  |  | O | [9 empty] | A
| O |  |  | 7 | Mid semester audio assets completed | [6 empty] | O | [7 empty] | A
|  | O |  | 8 | Final audio assets created | [9 empty] | O |  |  |  |  | A
| O | O |  | 9 | Main game finite state machine created | [5 empty] | O | [9 empty] | A
| O | O |  | 10 | Main tank finite state machine created | [5 empty] | O | [10 empty] | A
| O | O |  | 11 | Initial user interface created | [5 empty] | O | [11 empty] | A
|  | O |  | 12 | Final user interface created | [9 empty] | O | [5 empty] | A
|  | O |  | 13 | Bullets finite state machine created | [6 empty] | O | [9 empty] | A
|  | O |  | 14 | Enemy finite state machine and AI created | [6 empty] | O | [10 empty] | A
|  |  |  | 15 | MIDTERM DEMO | [7 empty] | O | [6 empty] | A | B | B | B
|  | O |  | 16 | Powerup 1 completed | [8 empty] | O | [6 empty] | A
|  | O |  | 17 | Powerup 2 completed | [8 empty] | O | [7 empty] | A
|  | O |  | 18 | Second game level completed | [8 empty] | O | [8 empty] | A
|  | O |  | 19 | Score board implemented | [10 empty] | O |  |  |  |  | A
|  | O |  | 20 | Boss implemented | [9 empty] | O | [6 empty] | A
|  |  | O | 21 | Playtesting among developers | [5 empty] | O | O |  |  |  | O |  |  |  | A | B | B | B
|  |  | O | 22 | Playtest with friends and gameplay tweaked | [6 empty] | O |  |  |  |  | O |  |  | A
|  |  | O | 23 | Schedule playtest with friends |  |  |  | O | [5 empty] | O |  |  |  |  | A
| O |  |  | 24 | Midterm powerpoint completed | [6 empty] | O | [7 empty] | A
|  | O |  | 25 | Final powerpoint completed | [11 empty] | O |  |  | A
| O | O | O | 26 | Regular demo integrated | [5 empty] | O | O | O | O | O | O | O |  |  | A | B
| O | O |  | 27 | Web site updated |  |  |  |  | O |  | O |  | O |  | O |  | O |  | A | B
|  | O |  | 28 | FINAL DEMO | [13 empty] | O | A | B | B | B
| O | O |  | 29 | Demo rehearsals | [6 empty] | O |  |  |  |  | O |  |  | A | B | B | B
# People working on the project:
Create design | Build Midterm Demo | Final Demo | Playtest and tune |  |  |  |  | 02/12 | 02/19 | 02/26 | 03/05 | 03/12 | 03/19 | 03/26 | 04/02 | 04/09 | 04/16 | 04/30 | 05/07 | Homer Simpson | Peter Griffin | Al Bundy | Philip Fry
[14 empty] | O | expected task activity here |  |  |  |  | A = primary owner
[14 empty] | O | no progress or stuck |  |  |  |  | B = secondary owner
[14 empty] | O | in progress
[14 empty] | O | completed
Version 03/19/2010 of the OPPM sheet
Adapted from OPPM: www.onepageprojectmanager.com
Major Tasks
Summary & Forecast
Objectives
Target Dates
Key